## Masterplan
As at 8th April 2021 (IAR)
CONSTRUCTION COSTS | Phase 1 | Q3 2021 | Phase 2 | Q3 2021 | Phase 3 | 2022/23 | Grand Total
(Estimated figures) | High Street | 38787 | PWE | 28145 | PWW | 60717
| Station Road | 14785 | Sevenoaks Road | 11379
|  |  | Shoreham Road | 11212
Individual phase costs |  | 53572 |  | 50736 |  | 60717 | 165025
FUNDING
Parish Developer Levy |  | 18571.24 |  | 22512.52 |  | 0 | 41083.76
KCC County Member fund |  | 5000 |  | 0 |  | 0 | 5000
KCC LTP funding |  | 30000 |  | 0 |  | 0 | 30000
District Developer Levy |  | 0 |  | 28224.24 |  | 21283.26 | 49507.5
TOTAL SECURED FUNDING |  | 53571.24 |  | 50736.76 |  | 21283.26 | 125591.26
Parish Developer Levy (projected) |  | 0 |  | 0 |  | 39433.74 | 39433.74
Total Funding Required Construction |  | 53571.24 |  | 50736.76 |  | 21283.26 | 165025
DESIGN & PROJECT MANAGEMENT
Design Fees & Disbursements | [6 empty] | 33157.39
Project Management (projected) | [6 empty] | 8251
Total Design & Project Management | [6 empty] | 41408.39
Notes:
Design & Project Management fees to be met by Parish Council
Construction costs to be met by grant funding and developer levies
TRAFFIC MANAGEMENT PROPOSALS
ESTIMATED IMPLEMENTATION SCHEDULE, COSTS & FUNDING